**Status of Your Community Air Monitoring Plan**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Shafter-DMV (PM2.5/PM10, VOC/PM2.5 Speciation)** | **Grimmway Academy (PM2.5)** | **Golden Oak Elementary School**  **(PM2.5)** | **Sequoia Elementary School**  **(Multi-Pollutant)** | **Shafter Farm Labor Center (Trailer)** | **La Colonia (PM2.5)\*** | **Areas of Interest with Air Monitoring Van (Multi-Pollutant)** |
| In Place | In Place | In Place | In Place | In place | In Progress | In Place |

**PM Monitoring:**

**Air Monitoring Van Activities** No van monitoring this week due to extreme heat. Insufficient power at site for maintaining proper equipment operating temperature.

**Understanding Toxics and Particulate Matter**24-hour samples of Toxics & PM2.5 speciation were taken on September 24th and 30th.

**Ongoing Implementation**

* La Colonia: signed lease agreement for installing PM2.5 monitor at 30715 Rodriguez Street; working with contractor to implement electrical infrastructure.